## Sheet1
IT-project plan with outsourcing | [30 empty] | Please consider drop of costs/hours by 5% annually
|  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7-12 |  |  |  | Month 13-24 |  |  |  | Month 25-36
|  |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore |  | On-shore |  | Off-shore
|  |  | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior | Senior | Junior
| % hours | Sum hours
Application helpdesk | 11% | 2480 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 14 | 20 | 78 | 116 | 78 | 116 | 208 | 312 | 208 | 312 | 184 | 276 | 184 | 276
Application management
Knowledge transfer | 10% | 2354 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 66 | 99 | 66 | 99 | 178 | 267 | 178 | 267 | 157 | 236 | 157 | 236
Major enhancements | 12% | 2896 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 13 | 20 | 78 | 120 | 78 | 120 | 224 | 336 | 224 | 336 | 196 | 296 | 196 | 296
Minor enhancements | 11% | 2648 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 11 | 18 | 72 | 114 | 72 | 114 | 204 | 308 | 204 | 308 | 180 | 272 | 180 | 272
Bug fixes | 11% | 2520 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 16 | 76 | 104 | 76 | 104 | 194 | 286 | 194 | 286 | 172 | 260 | 172 | 260
Project governance | 14% | 3154 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 88 | 132 | 88 | 132 | 236 | 354 | 236 | 354 | 212 | 321 | 212 | 321
Application operation | 13% | 2966 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 14 | 21 | 86 | 123 | 86 | 123 | 220 | 342 | 220 | 342 | 200 | 302 | 200 | 302
Infrastructure managment | 10% | 2354 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 12 | 17 | 66 | 99 | 66 | 99 | 178 | 267 | 178 | 267 | 157 | 236 | 157 | 236
Bookkeeping, administration | 8% | 1914 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 9 | 14 | 54 | 81 | 54 | 81 | 145 | 218 | 145 | 218 | 129 | 192 | 129 | 192
| 100% | 23286 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 112 | 167 | 664 | 988 | 664 | 988 | 1787 | 2690 | 1787 | 2690 | 1587 | 2391 | 1587 | 2391
Max number of person-hours |  | 27000
After you have calculated the personnel costs, add trevel and communication expenses 4% of the initial project costs
Then add contingency expenses (budget for unpredicted costs) 4% of the initial project costs
On-shore hourly rate including taxes
Senior employee | 120
Junior employee | 80
Off-shore hourly rate including taxes
Senior employee | 70
Junior employee | 50